## Sheet1
Project Exam 1
| Planning | [13 empty] | Designing | [6 empty] | Programming/Testing | [6 empty] | Implementation/Rollout
| 2019-05-13 | 2019-05-14 | 2019-05-15 | 2019-05-16 | 2019-05-17 | 2019-05-18 | 2019-05-19 | 2019-05-20 | 2019-05-21 | 2019-05-22 | 2019-05-23 | 2019-05-24 | 2019-05-25 | 2019-05-26 | 2019-05-27 | 2019-05-28 | 2019-05-29 | 2019-05-30 | 2019-05-31 | 2019-06-01 | 2019-06-02 | 2019-06-03 | 2019-06-04 | 2019-06-05 | 2019-06-06 | 2019-06-07 | 2019-06-08 | 2019-06-09 | 2019-06-10 | 2019-06-11 | 2019-06-12 | 2019-06-13 | 2019-06-14 | 2019-06-15 | 2019-06-16
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35
Read Assignment
Study information about SpaceX
Write down all planned activities
Make Gantt Chart
Make Functional Spec Document
Make Project Planning Document
Deliver work from week 1¦
Research for target audience
Make the target audience
Make Personas
Make Storyboards
Choose relevant API
Make Wireframe/Prototype
Deliver the work from second week
Make Moodboards
Make Skectes
Make Mockup
Make & Test Color Scheme
Sketch & Make buttons
Decide typography
Image Processing
SEO/Content
Check that the WCAG is good
Make final decision about the design
Build the HTML
Build HTML5 contact form
Include the semantics
Make CSS for desktop
Make CSS for mobil/tablet devices
Employ JavaScript & JSON API
Test pages
Make people test on different devices
Fix errors that may occur
Final Testing
Make Report
Deliver
Blue is milestores